## Sheet1
UL DBF 2022/23 | 2022 |  |  |  |  | 2023
| September | October |  | November | December | Januar | Februar |  | Marec |  |  | April
| « |  | « |  |  |  |  | « |  |  |  |  | «
REPORTS
Application
Proposal writing and submission
Report rough draft
Report editing and submission
PROTOTYPE 1
Concept
Analysis | [10 empty] | Planned Task
Sub-component design | [10 empty] | Planned Subtask
CAD model design | [9 empty] | « | Milestone
Manufacturing
Testing
PROTOTYPE 2
Design changes
CAD model correction
Manufacturing
Testing
COMPETITION MODEL
Final design changes
CAD model correction
Manufacturing
Testing
Aircraft optimisation
datumi
2022-09-07
2022-10-31
2022-02-25
2022-04-13